## Sheet1
Name |  | Man Hours Estimation | Actual Man Hours | Start Date | End Date | Responsibility | Remarks
Meeting Scheduler |  |  |  | 2017-04-03 | 2017-06-12
Define All Classes and Methods
| Chaos Monkey | 30 |  | 2017-04-07 | 2017-04-17 | Allen
| Janitor Monkey | 30 |  | 2017-04-07 | 2017-04-17 | David
| Conformity Monkey | 30 |  | 2017-04-07 | 2017-04-17 | Amity
| Client | 30 |  | 2017-04-07 | 2017-04-17 | Terry
| Resources | 30 |  | 2017-04-07 | 2017-04-17 | George
| Crawler | 30 |  | 2017-04-07 | 2017-04-17 | Joe
| Utility | 30 |  | 2017-04-07 | 2017-04-17 | Terry, George
Define Class-Class Relationship (Draw Class Diagram)
| Get togeher to draw | 6*6 |  | 2017-04-18 | 2017-04-25 | All | Get togher for 2 meetings to draw from scratch.
Class Cleanup
|  | 6*6 |  | 2017-04-25 | 2017-05-01 | All | Each person is reponsible for their assigned class(es).
Remove Duplicates (Design Principles)
| Seek reusibility opportunities | 6*6 |  | 2017-05-01 | 2017-05-08 | David (Supervise) | Polymorphism, inheritance, generalization.
Identify and/or Apply Design Patterns
|  |  |  | 2017-05-02 | 2017-05-26 | Terry (Supervise) | Yet to learn: to be updated.
Testing and Documentation
| Verify all is working well | 20 |  | 2017-05-26 | 2017-06-09 | George (Supervise) | Documentaiton includes presentaion materials.